| DEADLINE | COMMITTEE | WHO | ACTION |
| --- | --- | --- | --- |
|  | Governor Line | DG | Appoint Current Year Leadership Team and Assistant Governors. |
| Jul-15 | Nominating | IPDG | Update Nomination forms and other documents regarding DGND selection; update the page on the district’s website; schedule an informational meeting about the DGND selection Process; post a story on the website saying nominations are open and providing links to forms. |
| Jul-15 | Nominating | IPDG | Send note to Council of Governors seeking candidates for Vice-Governor for upcoming Nominating Committee selection meeting. |
| Jul-15 | Nominating | DG | Send Nominating Form for upcoming DGND selection to clubs. |
| Jul-15 | Governor Line | Immediate Past District Secretary | All District electronic records to be delivered to Current District Secretary by July 15. |
| Jul-31 | Finance | IPDG | Submit final financial spending report for DG expenses to Club and District Support. |
| Jul-31 | Governor Line | IPDG | Complete and finalize club ratings in My Rotary. |
| Jul-31 | Finance | District Youth Exchange Chair | Provide DGE with a financial report for the just completed year. |
| Aug-25 | Nominating | IPDG | Earliest date for Vice-Governor Interest Letter to be required to be submitted. |
| Aug-31 | Finance | District Treasurer | Submit final financial report for past year to DG, DGE, DGN and the Finance Committee. |
| Sep-1 | Nominating | IPDG | Earliest Date for District Governor Nomination Form to be required to be submitted. |
| 1 week prior to Nominating Committee meeting | Nominating | IPDG | Forward logistics and instructions to Nominating Committee, including sample questions. |
| Sep-8 | Nominating | IPDG | Earliest date for Nominating Committee selection meeting. |
| Sep-30 | Finance | Immediate Past District Treasurer | Last Day for Immediate Past Treasurer to to submit report on separate accounts to Governor. |
| Oct-1 | Nominating | IPDG | Latest Date for Vice-Governor Interest Letter to be required to be submitted. |
| Oct-8 | Nominating | IPDG | Latest Date for District Governor Nomination Form to be required to be submitted. |
| Oct-15 | Nominating | IPDG | Latest date for Nominating Committee selection meeting. |
| Day after Nominating Committee Meeting | Nominating | IPDG | Notify candidates; Notify DG of the candidate selected within 24 hours of the meeting; forward written report to DG on behalf of the Nominating Committee within 2 days. |
| Within 72 hours of Nominating Committee meeting | Nominating | DG | Publish name and club of selected candidate. |
| 14 days after publication of name of DGND | Nominating | DG | Deadline for challenges to the candidate selected by the Nominating Committee; if no challenges, declare selection of DGND. |
| Within 10 days of declaring selection of DGND | Nominating | DG | Submit Governor Nominee Designate form to Club and District Support. |
| Oct-30 | Finance | District Treasurer | Provide quarterly financial report to DG, DGE, DGN, DGND, and Finance Committee. |
| Nov-15 | Finance | District Youth Exchange Chair and RYLA Chair | Provide DGE with a budget for the upcoming Rotary Year. |
| Dec-22 | Finance | DGE Finance Committee Chair | Finance Committee to meet no later than today to review the proposed budget submitted by the DGE. Finance Committee Chair shall give notice of this meeting no later than 30 days in advance. |
| Dec-31 | Youth Service | Youth Service Subcommittee Chairs | Send written report to Youth Service Chair |
| Dec-31 | Finances | District Treasurer | Completion of external financial audit, unless extended by Finance Committee |
| Jan-15 | Nominating | DG | DG to announce date for Nominating Committee to select next District Governor; must be between September 8 and October 15. |
| Jan-15 | Nominating | IPDG | IPDG to appoint Primary Committee; and names to be published by DG on the District website, with a request to clubs to offer candidates for the Nominating Committee. |
| Jan-30 | Financials | District Treasurer | Provide quarterly financial report to DG, DGE, DGN, DGND, and Finance Committee |
| 30 days prior to PETS | Finance | DGE | Last day for DGE proposed budget and dues to be distributed to Presidents-Elect. That budget shall have been reviewed earlier by the Finance Committee and recommended to the PEs. |
| Prior to March 1 | Legislative | Legislative Committee Chair | Meet with the Governors Line at least four months prior to their taking office to discuss the MoP and Bylaws of the Corporation |
| At least 30 days prior to the Annual Business Meeting | Nominating | Primary Committee DG | Send proposed Nominating Committee to DG; names to be published by DG to the clubs in a timely manner |
| More than 30 days prior to Annual Business Meeting | Legislative | Legislative Committee | Proposed resolutions or amendments to governing documents must be submitted in writing to the DG. |
| 30 days prior to Annual Business Meeting | Governor Line | DG | DG publishes proposals to clubs in the district. |
| Apr-30 | Financials | District Treasurer | Provide quarterly financial report to DG, DGE, DGN, DGND, and Finance Committee |
| May-1 | Youth Service | DGE | Complete Rotary Youth Exchange certification renewal form and requirements, if we intend to participate for the upcoming year. |
| Prior to Annual Business and Corporation Board meetings, but not later than 30 June | Finance | District Treasurer | Prepare resolution for Board adoption identifying who will have checking signature authority in the new Rotary year. |
| Jun-30 | Youth Service | Youth Service Subcommittee Chairs | Send written report to Youth Service Chair |
| Jun-30 | Governor Line | IPDG | Deadline for naming members to the Finance Committee to replace those whose term is up. |
| Jun-30 | Governor Line | DG | Last date for District Annual Business Meeting |
| Jun-30 | Governor Line | DG | Last date for Annual Meeting of the Corporation Board |